## Gantt Chart
Months | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
Action Item/Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
1.REQUIREMENT GATHERING | 8 Weeks
Project Scope,Meeting Internal Management and Stakeholders
1.1 Identify and Understand of the SRS, BRS and FRS document
1.2 Create all three-requirement document
1.3 Review the Requirements
1.4 Final Approval from the Stakeholders and owners
2.Design | [8 empty] | 8 Weeks
2.1 Detailed user documentation and identifying features
2.2 Detailed user documentation for system architecture & system design
2.3 Determining the priority order of the proposed work, building a product roadmap, and obtaining stakeholder agreement on it
3.Implement Phase and Development | [16 empty] | 12 Weeks
3.1 Start development as per the features priority
3.2 Once the individual features are ready do the integration and end to end development
3.3 Unit Testing
3.4 Ready for Testing
4.Testing | [27 empty] | 8 Weeks
4.1 Start Designing the Testcases based on the SRS and FRS Document
4.2 Functional Testing
4.3 Integration Testing
4.4 End to End Testing
4.5 Cover all the requirements and map with the Requirement Traceability matrix
4.6 Defect Retest
5. Deploy | [36 empty] | 2 Weeks
5.1 Deploy in Pre-Prod and do the Smoke Testing
5.2 Deploy and release the software to the production environment
HEMANT CHOWDARY - 0788804
NISHI SHRIVASTAVA - 0770047
PRAYAS BALIYAN - 0790447
KIRAN PATHURI - 0788366
SAI KRISHNA - 0789428