## RACI
Role Activity | CFO | Stakeholders | Business Analysts | Solution Architect | Procurement Manager | Infrastructure Operation | Development Manager | Testing Manager | Project Manager | Dev ops Manager | Support/ Performance Team | R - responsible A - accountable C - consulted I - informed
1. Requirement Gathering
1.1 - Identify the Business Requirements | I | C | I | [5 empty] | C,I
1.2 - Understand the Business Requirements | I | C | R | [5 empty] | C,I
1.3 - Meeting with Stakeholders for the finalizing the requirments | C,I | C,I | R | [5 empty] | C,I
1.4 - Create the SRS, BRS and FRS document | I | I | R | R |  |  |  |  | C,I
1.5 - Review the Requirements and Final Approval from the Stakeholders and owners | I | C,I | A,R | C,I |  |  |  |  | R,A,C,I
2. Infrastructure (Procurement, Setup and Configuration)
2.1 - Identify the Development tool for starting implementaion | I | I | I |  | R,A | R,A | R |  | C,I
2.2 - Identify the Testing Tool for testing the Application | I | I | I |  | R,A | R,A |  | R | C,I
2.3 - Deployment Tools | I | I | I |  | R,A | R,A | R |  | C,I
2.4 - Maintaining Code Reporsitories | I | I | I |  |  | R,A | R,A | R,A | C,I
2.5 - Maintaining Testing Reporsitories and Artifacts | I | I | I |  |  |  |  | R,A | C,I
2.6 - Maintaining the Requirement Artifacts tool and approval | I | I | R |  | A | A | I | I | C,I
2.7 - Development Devices for Unit Testing | I | I | I |  | A | A | A,I |  | C,I
2.8 - Testing iOS and Andriod Devices for Testing | I | I | I |  | A |  |  | A,I | C,I
2.9 - Set up the Environement for Development, Testing and Deployment | I | I | I |  |  | R,A | R,A | R,A | C,I
3. Development
3.1 - UI and UX Designer |  |  | I | C,I |  |  | R,A |  | C,I
3.2 - BackEnd Development |  |  | I | C,I |  |  | R,A |  | C,I
3.3 - Create the Development Framework | [6 empty] | R,A |  | C,I | R
3.4 - Create the Usable Functions for all the application pages | [6 empty] | R,A |  | C,I
3.5 - Integrate all the application pages functionalities | [6 empty] | R,A |  | C,I
3.6 - Unit Testing and Review the Code | [6 empty] | R,A |  | C,I
3.7 - Signoff from the Development Lead for start the Testing | I | I,C | I,C |  |  |  | R,A |  | C,I |  | R,A
4. Testing
4.1 - Design the Functional,Integration, End to End TestCases | I | I | A | R | R |  |  | R,A | C,I
4.2 - Review the TestCases and take a Signoff before the execution | I | I | A | R | R |  |  | R,A | C,I
4.3 - Execute the Functional,Integration, End to End TestCases | I | I | I | A | R |  |  | R,A | C,I
4.4 - Defect Tracking |  | I,C | I,C |  |  |  |  | R,A | C,I
4.5 - Maintain all the Testing Artifacts and Repositories | I | I,C | I,C |  |  |  |  | R,A | C,I
4.6 - Testing Signoff and good to go for Deployment | I | I,C | I,C |  |  |  |  | R,A | C,I
5. Deployment
5.1 - Create the CI/CD Pipeline for the Deployment |  | I | [6 empty] | C,I | R,A
5.2 - Schedule the jobs and trigger the build for Release |  | I | [6 empty] | C,I | R,A
5.3 - Sanity Testing on Pre Prod Env |  | I | [6 empty] | C,I | R,A
5.4 - Deploy the Final Build on Production Env | I | I,C | I |  |  |  | I | I | C,I | R,A
5.5 - Deployment Signoff | I | I,C | I | [5 empty] | C,I | R,A
6. Maintanance
6.1 - Application Maintance and Monitor the Performance of the Application | I | I | I |  |  |  | I | I | C,I | I | R,A
6.2 - Enhancement or New Changes | I | I,C | I,C |  |  |  | R,A | R,A | C,I | I | R,A
HEMANT CHOWDARY - 0788804
NISHI SHRIVASTAVA - 0770047
PRAYAS BALIYAN - 0790447
KIRAN PATHURI - 0788366
SAI KRISHNA - 0789428