## WAC
RESOURCE WORK ACTIVITIES CHART
TASK | START DATE | END DATE | DURATION in days
1.REQUIREMENT GATHERING
Project Scope,Meeting Internal Management and Stakeholders
1.1 Identify and Understand of the SRS, BRS and FRS document | 2023-01-01 | 2023-01-15 | 14
1.2 Create all three-requirement document | 2023-01-16 | 2023-01-31 | 15
1.3 Review the Requirements | 2023-02-01 | 2023-02-15 | 14
1.4 Final Approval from the Stakeholders and owners | 2023-02-16 | 2023-02-28 | 12
2.Design
2.1 Detailed user documentation and identifying features | 2023-03-01 | 2023-03-22 | 21
2.2 Detailed user documentation for system architecture & system design | 2023-03-23 | 2023-04-15 | 23
2.3 Determining the priority order of the proposed work, building a product roadmap, and obtaining stakeholder agreement on it | 2023-04-16 | 2023-04-30 | 14
3.Implement Phase and Development
3.1 Start development as per the features priority | 2023-05-01 | 2023-06-30 | 60
3.2 Once the individual features are ready do the integration and end to end development | 2023-07-01 | 2023-07-15 | 14
3.3 Unit Testing | 2023-07-16 | 2023-07-31 | 15
3.4 Ready for Testing | 2023-07-31 | 2023-07-31
4.Testing
4.1 Start Designing the Testcases based on the SRS and FRS Document | 2023-08-01 | 2023-08-15 | 14
4.2 Functional Testing | 2023-08-16 | 2023-08-30 | 14
4.3 Integration Testing | 2023-09-01 | 2023-09-15 | 14
4.4 End to End Testing | 2023-09-16 | 2023-09-25 | 9
4.5 Cover all the requirements and map with the Requirement Traceability matrix | 2023-09-26 | 2023-09-30 | 4
4.6 Defect Retest | 2023-10-01 | 2023-10-06 | 5
5. Deploy
5.1 Deploy in Pre-Prod and do the Smoke Testing | 2023-10-07 | 2023-10-15 | 8
5.2 Deploy and release the software to the production environment | 2023-10-16 | 2023-10-23 | 7
HEMANT CHOWDARY - 0788804
NISHI SHRIVASTAVA - 0770047
PRAYAS BALIYAN - 0790447
KIRAN PATHURI - 0788366
SAI KRISHNA - 0789428
Formulas:
END DATE = [START DATE]+21